## How to use
Spend management implementation plan - Template
In the first tab, you will find the Implementation timeline for the Yokoy suite. Feel free to adjust it to fit your own planning.
The second tab is the Hypercare checklist. After the implementation and Go-live, the Yokoy team assists you for one more month - this is the Hypercare phase.
If you have questions about our implementation timeline, or want to know more about the Yokoy suite's functionality, feel free to contact us.
More information: | yokoy.io

## Yokoy implementation plan
Sample Yokoy implementation plan
[6 empty] | Project title | Yokoy implementation - WAVE 1
[6 empty] | Implementation | [Partner name]
Ownership [client] |  |  | Ownership Yokoy
Sponsor |  | [Name] | [Name] |  |  | Dates
Project manager |  | [Name] | [Name] |  |  | Go live | [Date]
Technical lead |  | [Name] | [Name] |  |  | Target | [Date]
STATUS [Not started, In progress, Done, Blocked] | STEP | TASK | TASK OWNER |  | DEPENDENCIES | START DATE | DUE DATE | DURATION (DAYS) |  | PHASE ONE |  |  |  |  | PHASE TWO | [32 empty] | PHASE THREE
|  |  |  | COMMENTS |  |  |  |  | DELIVERABLES | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18
[10 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
| 1 | Project management
Done | 1.1 | Kick-off | [Name]
In progress | 1.2 | Weekly project updates & admin | [Name]
| 2 | Workstream Yokoy configuration
Blocked | 2.1 | Define business/finance settings for Yokoy | [Name]
Not started | 2.2 | Definition of the required master data (user + cost objects) | [Name]
| 2.3 | Validation of business requirements by Yokoy, Q&A | [Name]
| 2.4 | Configuration of customer-specific features and configuration of Yokoy Test (sandbox) | [Name]
| 2.5 | Definition & Setup Approval Flow Expenses | [Name]
| 3 | Workstream configuration interfaces
| 3.1 | Definition system architecture | [Name]
| 3.2 | ERP interface (cost objects & user data) | [Name]
| 3.3 | ERP interface (expense accounting) | [Name]
| 3.4 | Archiving expense receipts | [Name]
| 4 | Workstream credit card integration
| 4.1 | Inquiry to credit card provider | [Name]
| 4.2 | Data receipt from credit card providers with data control | [Name]
| 4.3 | Set up import credit card data in Yokoy | [Name]
| 5 | Workstream IT & Security Setup
| 5.1 | IT whitelisting of Yokoy domains | [Name]
| 5.2 | Setting up SSO | [Name]
| 6 | Testing & Training
| 6.1 | Back office training | [Name]
| 6.2 | Testing workflow in sandbox & sign-off | [Name]
| 6.3 | Testing ERP data flow & sign-off (cost objects and user data) | [Name]
| 6.4 | Testing ERP data flow & sign-off (expense accounting) | [Name]
| 6.5 | Testing approval flow expenses | [Name]
| 7 | Workstream shift into production/go-live
| 7.1 | Configuration of customer-specific features and configuration of Yokoy production | [Name]
| 7.2 | Deployment into ERP production | [Name]
| 7.3 | Deployment in the prod by Yokoy | [Name]
| 7.4 | Go-live support | [Name]
| CR | Change requests
| CR1 | [Description] | [Name]
| CR2 | [Description] | [Name]
| CR3 | [Description] | [Name]
| CR4 | [Description] | [Name]

## Hypercare checklist
Sample Hypercare checklist
| Go live date: |  | [Date]
| End of Hypercare date: |  | [Date]
| Task ID | Task Domain | Action | Action Description | Status [Not started, In progress, Done, Blocked]
1 | GE-01 | General | Feedback | We are aware that our general feedback was forwarded to Product Management to analyse an implementation, but no specific timeline and gurantee of implementatn can be given. | Done
2 | GE-02 | General | Open points list | There are no open points relating back to the onboarding phase or Go-live. | In progress
3 | GE-03 | General | Support | For any operational topics and questions (e.g. an user can't login) we contact support@yokoy.ai. We will get a reply within 24 hours. We know, that our Implementation Manager is after the Hypercare no longer our contact person. | Blocked
4 | GE-05 | General | Account Management | For any account related questions (e.g. More licenses needed) we contact accountmanagement@yokoy.ai We know, that our Implementation Manager is after the Hypercare no longer our contact person. | Not started
5 | TR-01 | Training | Training | During the Onboarding Project we got trained how to use Yokoy on the different roles: Submitter, Manager, Finance & Admin role. | Not started
6 | TR-03 | Training | Training Transactions | We got trained on how to handle transactions and the related matching | Not started
7 | TR-04 | Training | Training Admin Menu | We know how to setup new items (e.g. VAT rates, categories) in the Admin Menu. | Not started
8 | TR-05 | Training | Training Submitter | We did a training for our employees and showed them the functionalities within the submitter menu. They know how to submitt an expense and how the approval flow works. | Not started
9 | TR-06 | Training | Training Assistant | We did a training for our employees and showed them the functionalities within the assistant menu. They know how to submitt an expense and how the approval flow works. | Not started
10 | TR-07 | Training | Training Manager | We did a training for our Managers and showed them the functionalities within the manager menu. They know how to approve an expense. | Not started
11 | TR-08 | Training | Training Manager Delegate | We did a training for our Delegates of Managers and showed them the functionalities within the manager menu. They know how to approve an expense. | Not started
12 | TR-09 | Training | Help Center | We know where to find the Helpcenter and how to search for topics. Also our employees know that they find first level support there. | Not started
13 | TR-10 | Training | Documentation / Guides | We received from our Implementation Manager manuals for the Finance & Admin Menu. | Not started
14 | TR-13 | Training | Train the trainer Approach | We understand that Yokoy follows the "train the trainer" approach. Therefore the employees contact the dedicated person within our company and not Yokoy directly. | Not started
15 | IM-01 | Import | Import of User | We can successfully import users and adjust them. | Not started
16 | EX-01 | Export | Export privately paid Expenses | We can successfully export privately paid expenses and they are correctly booked in our ERP. This includes trips, mileage rates and lump sums. | Not started
17 | EX-02 | Export | Export Company Credit Card Transactions | We can successfully export transactions paid with the company credit card and they are correctly booked in our ERP. | Not started
18 | EX-03 | Export | Export Credit Notes | We know how to handle and match credit notes. We can successfully export them and they are correctly booked in our ERP. | Not started
19 | TS-01 | Technical Setup | sFTP Connection - Export | We have access to the sFTP facility and export of the file via sFTP is working. | Not started
20 | TS-02 | Technical Setup | sFTP Connection - Import | We have access to the sFTP facility and import of the file via sFTP is working. | Not started
21
22
[Date]
We hereby confirm that I/we have understood and completed the necessary "Hypercare" tasks in order to ensure smooth operations while using Yokoy. We understand and acknowledge the following: - Change requests and other aspects can be added upon request and are billed on an actual-effort basis at an agreed hourly rate. The effort estimate is based on similar projects, and may require a new Order Form. - We, as the client, are responsible for meeting all regulatory requirements. - We, as the client, confirm that the Yokoy software is configured correctly. We assume full ownership of maintaining the software configuration to our needs.
Signature 1
Title
Name
Date
Signature 2
Title
Name
Date